## Group 1 (hidden)
VENDOR DECORATION PROJECT TRACKER
Project: | Sunny Islea Beac FL |  |  |  | Client: |  |  |  |  | PM / Owner:
Start Date: |  |  |  |  | Install Date: | By 11/12 |  |  |  | Currency: | USD
Area | # | Decoration | Qty | Vendor | Link | Material Pricing |  | Labor Pricing |  | Item Total | Status | Approval | Notes | Last Updated
[6 empty] | Unit | Total | Unit | Total
A1A Street Pole Decor & Collins Ave (Median) | [5 empty] | Section Subtotal → |  |  |  | 68410
Area 1 | 1 | Medjool Palm Trees (Medium) | 56 | Be The Light |  |  | 0 | 240 | 13440 | 13440 | Completed |  | 6 strands each tree. 6*40 = 240 per tree
Area 1 | 2 | Royal Palm Trees | 92 | Be The Light |  |  | 0 | 320 | 29440 | 29440 | Completed |  | 8 strands each tree 8*40 = 320 per tree
Area 1 | 3 | 6' Candy Cane Swirl PM | 15 | Display Sales | CC Swirl | 323 | 4845 | 100 | 1500 | 6345 | Completed |  | PM STANDS FOR POLE MOUNT
Area 1 | 4 | 6' Gift Box PM | 15 | Display Sales | Gift box | 333 | 4995 | 100 | 1500 | 6495 | Completed
Area 1 | 5 | 6' Snowman PM | 15 | Display Sales | https://displaysales.com/products/6-ft-snowman-christmas-pole-mounted-decoration?variant=52151903191221 | 351 | 5265 | 100 | 1500 | 6765 | Completed
Area 1 | 6 | 6' Zig Zag Tree PM | 15 | Display Sales | zig zag | 295 | 4425 | 100 | 1500 | 5925 | Completed
Area 1 | 7 | 6' Double Poinsettia PM | 15 | Display Sales | double poinsettia | 317 | 4755 | 100 | 1500 | 6255 | Completed
Area 1 | 8 | 6' Single Bell PM | 15 | Display Sales | single bell | 304 | 4560 | 100 | 1500 | 6060 | Completed
Area 1 | 9 | 6' Stocking PM | 15 | Display Sales | stocking | 279 | 4185 | 100 | 1500 | 5685 | Completed
Area 1 | 10 | 6' Angel with Halo PM | 14 | Display Sales | angel | 339 | 4746 | 100 | 1400 | 6146 | Completed
Area 1 | 11 | 6' Candy Cane with Bow PM | 14 | Display Sales | candy cane w bow | 304 | 4256 | 100 | 1400 | 5656 | Completed
Area 1 | 12 | 6; Candle with Halo PM | 14 | Display Sales | candle w halo | 278 | 3892 | 100 | 1400 | 5292 | Completed
Area 1 | 13 | 6 Toy Soldier PM | 14 | Display Sales | toy soldier | 346 | 4844 | 100 | 1400 | 6244 | Completed
Area 1 — Subtotal | [6 empty] | 19530 |  | 48880 | 68410
Sunny Isles East Boulevard (163rd St E Bound) | [5 empty] | Section Subtotal → |  |  |  | 23117
Area 2 | 8 | Medjool Palm Trees | 65 | Be The Light |  |  | 0 | 240 | 15600 | 15600 | Completed
Area 2 | 9 | Various Palms | 1 | Be The Light |  |  | 0 | 1000 | 1000 | 1000 | Completed
Area 2 | 10 | 6' Reindeer PM | 5 | Display Sales | reindeer | 323 | 1615 | 100 | 100 | 1715 | Completed
Area 2 | 11 | 6' Christmas Tree PM | 5 | Display Sales | xmas tree | 254 | 1270 | 100 | 500 | 1770 | Completed
Area 2 | 12 | 6' Candy Cane Swirl PM | 4 | Display Sales | CC Swirl | 323 | 1292 | 100 | 400 | 1692 | Completed
Area 2 | 13 | 6' Stocking PM | 4 | Display Sales | stocking | 235 | 940 | 100 | 400 | 1340 | Completed
Area 2 — Subtotal | [6 empty] | 5117 |  | 18000 | 23117
North Bay Road | [5 empty] | Section Subtotal → |  |  |  | 7087
Area 3 | 8 | 5.5' 4 Falling Star PMs | 19 | Display Sales | falling stars | 273 | 5187 | 100 | 1900 | 7087 | Completed
Area 3 | 9 | [5 empty] | 0 |  | 0 | 0
Area 3 | 10 | [5 empty] | 0 |  | 0 | 0
Area 3 | 11 | [5 empty] | 0 |  | 0 | 0
Area 3 | 12 | [5 empty] | 0 |  | 0 | 0
Area 3 | 13 | [5 empty] | 0 |  | 0 | 0
Area 3 — Subtotal | [6 empty] | 5187 |  | 1900 | 7087
172nd | [5 empty] | Section Subtotal → |  |  |  | 4606
Area 4 | 8 | 4' Diamond Snow flakes PM | 14 | Display Sales | diamond | 229 | 3206 | 100 | 1400 | 4606 | Completed
Area 4 | 9 | [5 empty] | 0 |  | 0 | 0
Area 4 | 10 | [5 empty] | 0 |  | 0 | 0
Area 4 | 11 | [5 empty] | 0 |  | 0 | 0
Area 4 | 12 | [5 empty] | 0 |  | 0 | 0
Area 4 | 13 | [5 empty] | 0 |  | 0 | 0
Area 4 — Subtotal | [6 empty] | 3206 |  | 1400 | 4606
174th | [5 empty] | Section Subtotal → |  |  |  | 7866
Area 5 | 8 | 6' Candy Cane Swirl PM | 10 | Display Sales | CC Swirl | 323 | 3230 | 100 | 1000 | 4230 | Completed
Area 5 | 9 | 6' Candy Cane Bow PM | 9 | Display Sales | candy cane w bow | 304 | 2736 | 100 | 900 | 3636 | Completed
Area 5 | 10 | [5 empty] | 0 |  | 0 | 0
Area 5 | 11 | [5 empty] | 0 |  | 0 | 0
Area 5 | 12 | [5 empty] | 0 |  | 0 | 0
Area 5 | 13 | [5 empty] | 0 |  | 0 | 0
Area 5 — Subtotal | [6 empty] | 5966 |  | 1900 | 7866
Gateway Park (151 Sunny Isles Blvd) | [5 empty] | Section Subtotal → |  |  |  | 66026
Area 6 | 8 | Oak Trees (trunk & canopy) | 22 | Be The Light |  |  | 0 | 600 | 13200 | 13200 | Completed |  | 15 strands per tree *40 per strand = 600/
Area 6 | 9 | Date Palms | 8 | Be The Light |  |  | 0 | 240 | 1920 | 1920 | Completed |  | 6 strands each tree. 6*40 = 240 per tree
Area 6 | 10 | 6' Menorah Ground Mount | 1 | Display Sales | menorah | 721 | 721 | 100 | 100 | 821 | Completed
Area 6 | 11 | 17' Walkthrough Package with Bow | 1 | Display Sales | Walkthrough package | 17415 | 17415 | 500 | 500 | 17915 | Completed
Area 6 | 12 | 34' Panel Tree | 1 | Display Sales | panel tree | 28188 | 28188 | 3000 | 3000 | 31188 | Completed
Area 6 | 13 | 4' 3D Nativity Star Top | 1 | Display Sales | tree topper | 882 | 882 | 100 | 100 | 982 | Completed
Area 6 | 14 | 10' Santa Deluxe Sleigh Photo Op | 1 | Display Sales | Sleigh | 21560 | 21560 | 250 | 250 | 21810 | Completed
Area 6 — Subtotal | [6 empty] | 47206 |  | 18820 | 66026
159th St | [5 empty] | Section Subtotal → |  |  |  | 4194
Area 7 | 9 | 6' Triple Star PM | 9 | Display Sales | triple star | 366 | 3294 | 100 | 900 | 4194 | Completed
Area 7 | 10 | [5 empty] | 0 |  | 0 | 0
Area 7 | 11 | [5 empty] | 0 |  | 0 | 0
Area 7 | 12 | [5 empty] | 0 |  | 0 | 0
Area 7 | 13 | [5 empty] | 0 |  | 0 | 0
Area 7 | 14 | [5 empty] | 0 |  | 0 | 0
Area 7 — Subtotal | [6 empty] | 3294 |  | 900 | 4194
Nort Bay Padestrian Bridge | [5 empty] | Section Subtotal → |  |  |  | 2672
Area 8 | 9 | 4' Designer Star | 8 | Display Sales | designer star | 234 | 1872 | 100 | 800 | 2672
Area 8 | 10 | [5 empty] | 0 |  | 0 | 0
Area 8 | 11 | [5 empty] | 0 |  | 0 | 0
Area 8 | 12 | [5 empty] | 0 |  | 0 | 0
Area 8 | 13 | [5 empty] | 0 |  | 0 | 0
Area 8 | 14 | [5 empty] | 0 |  | 0 | 0
Area 8 — Subtotal | [6 empty] | 1872 |  | 800 | 2672
AREA 9 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 9 | 9 | [5 empty] | 0 |  | 0 | 0
Area 9 | 10 | [5 empty] | 0 |  | 0 | 0
Area 9 | 11 | [5 empty] | 0 |  | 0 | 0
Area 9 | 12 | [5 empty] | 0 |  | 0 | 0
Area 9 | 13 | [5 empty] | 0 |  | 0 | 0
Area 9 | 14 | [5 empty] | 0 |  | 0 | 0
Area 9 — Subtotal | [6 empty] | 0 |  | 0 | 0
AREA 10 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 10 | 9 | [5 empty] | 0 |  | 0 | 0
Area 10 | 10 | [5 empty] | 0 |  | 0 | 0
Area 10 | 11 | [5 empty] | 0 |  | 0 | 0
Area 10 | 12 | [5 empty] | 0 |  | 0 | 0
Area 10 | 13 | [5 empty] | 0 |  | 0 | 0
Area 10 | 14 | [5 empty] | 0 |  | 0 | 0
Area 10 — Subtotal | [6 empty] | 0 |  | 0 | 0
LOGISTICS | [5 empty] | Section Subtotal → |  |  |  | 26579
Logistics | 9 | Shipping | 1 | Display Sales |  | 16579 | 16579 |  | 0 | 16579 | Completed
Logistics | 10 | Storage | 1 | Be The Light |  |  | 0 | 8000 | 8000 | 8000 | Completed
Logistics | 11 | Maintenance | 1 |  |  |  | 0 | 2000 | 2000 | 2000
Logistics | 12 | Traffic Control | 1 |  |  |  |  | 2500 | 2500
Logistics | 13 | [5 empty] | 0 |  | 0 | 0
Logistics — Subtotal | [6 empty] | 16579 |  | 12500 | 26579
GRAND TOTAL (All Areas + Logistics) | [5 empty] | Total → |  |  |  | 210557
-
[6 empty] | MATERIAL | 89506
[6 empty] | SHIPPING | 16579

## Group 2 (hidden)
VENDOR DECORATION PROJECT TRACKER
Project: | Sunny Islea Beac FL |  |  |  | Client: |  |  |  |  | PM / Owner:
Start Date: |  |  |  |  | Install Date: | By 11/12 |  |  |  | Currency: | USD
Area | # | Decoration | Qty | Vendor | Link | Material Pricing |  | Labor Pricing |  | Item Total | Status | Approval | Notes | Last Updated
[6 empty] | Unit | Total | Unit | Total
Park Lighting - Heritage Park (19200 Collins Ave) | [5 empty] | Section Subtotal → |  |  |  | 6240
Area 1 | 1 | Medjool Palm Trees (Trunk & Fronds) | 26 | Be The Light |  |  | 0 | 240 | 6240 | 6240 | Completed |  | 6 strands each tree. 6*40 = 240 per tree
Area 1 | 2 | [5 empty] | 0 |  | 0 | 0
Area 1 | 3 | [5 empty] | 0 |  | 0 | 0
Area 1 | 4 | [5 empty] | 0 |  | 0 | 0
Area 1 | 5 | [5 empty] | 0 |  | 0 | 0
Area 1 | 6 | [5 empty] | 0 |  | 0 | 0
Area 1 — Subtotal | [6 empty] | 0 |  | 6240 | 6240
Park Lighting - Samson Park (17425 Collins Ave) | [5 empty] | Section Subtotal → |  |  |  | 12240
Area 2 | 1 | Medjool Palm Trees (trunk & fronds) | 11 | Be The Light |  |  | 0 | 240 | 2640 | 2640 | Completed
Area 2 | 2 | Palm Trees (coconut/triple christmas) | 40 | Be The Light |  |  | 0 | 240 | 9600 | 9600 | Completed
Area 2 | 3 | [5 empty] | 0 |  | 0 | 0
Area 2 | 4 | [5 empty] | 0 |  | 0 | 0
Area 2 | 5 | [5 empty] | 0 |  | 0 | 0
Area 2 | 6 | [5 empty] | 0 |  | 0 | 0
Area 2 — Subtotal | [6 empty] | 0 |  | 12240 | 12240
Park Lighting - Intracoastal SPorts Park (Collins Ave 159 to 163rd St) | [5 empty] | Section Subtotal → |  |  |  | 14400
Area 3 | 1 | OPTIONAL Tree Lighting - Open to Proposal |  | Be The Light |  |  | 0 |  | 0 | 0
Area 3 | 2 | Palms | 60 |  |  |  | 0 | 240 | 14400 | 14400
Area 3 | 3 | [5 empty] | 0 |  | 0 | 0
Area 3 | 4 | [5 empty] | 0 |  | 0 | 0
Area 3 | 5 | [5 empty] | 0 |  | 0 | 0
Area 3 | 6 | [5 empty] | 0 |  | 0 | 0
Area 3 — Subtotal | [6 empty] | 0 |  | 14400 | 14400
Park Lighting - The Spot (215 185th St) | [5 empty] | Section Subtotal → |  |  |  | 1230
Area 4 | 1 | Medjool Palm Trees (trunk & fronds) | 2 | Be The Light |  |  | 0 | 240 | 480 | 480 | Completed
Area 4 | 2 | Lights on front Building facade | 1 | Be The Light |  |  | 0 | 750 | 750 | 750 | Completed
Area 4 | 3 | [5 empty] | 0 |  | 0 | 0
Area 4 | 4 | [5 empty] | 0 |  | 0 | 0
Area 4 | 5 | [5 empty] | 0 |  | 0 | 0
Area 4 | 6 | [5 empty] | 0 |  | 0 | 0
Area 4 — Subtotal | [6 empty] | 0 |  | 1230 | 1230
Town Center Park (17200 Colins Ave) | [5 empty] | Section Subtotal → |  |  |  | 13500
Area 5 | 1 | OPTIONAL Tree Lighting - Open to Proposal | 0 | Be The Light |  |  | 0 | - | 0 | 0 | Completed
Area 5 | 2 | Palms | 40 |  |  |  | 0 | 300 | 12000 | 12000
Area 5 | 3 | Pavillions light up | 1 |  |  |  | 0 | 1500 | 1500 | 1500
Area 5 | 4 | [5 empty] | 0 |  | 0 | 0
Area 5 | 5 | [5 empty] | 0 |  | 0 | 0
Area 5 | 6 | [5 empty] | 0 |  | 0 | 0
Area 5 — Subtotal | [6 empty] | 0 |  | 13500 | 13500
Facilities - Government Center (18070 Colins Ave) | [5 empty] | Section Subtotal → |  |  |  | 2698
Area 6 | 1 | Exterior - Medjool Palm (trunk&frond) | 6 | Be The Light |  |  | 0 | 300 | 1800 | 1800 | Completed
Area 6 | 2 | Indoor - 10' Christmas Tree Douglas Fir with WW LED Bulbs 5mm | 1 | Display Sales | indoor tree | 698 | 698 | 200 | 200 | 898 | Completed
Area 6 | 3 | [5 empty] | 0 |  | 0 | 0
Area 6 | 4 | [5 empty] | 0 |  | 0 | 0
Area 6 | 5 | [5 empty] | 0 |  | 0 | 0
Area 6 | 6 | [5 empty] | 0 |  | 0 | 0
Area 6 — Subtotal | [6 empty] | 698 |  | 2000 | 2698
Pelican Community Park (18155 North Bay Road) | [5 empty] | Section Subtotal → |  |  |  | 458
Area 7 | 1 | Interior - 6.5' Christmas Tree Douglas Fir with WW LED Bulbs 5mm | 1 | Display Sales | indoor tree | 358 | 358 | 100 | 100 | 458 | Completed
Area 7 | 2 | [5 empty] | 0 |  | 0 | 0
Area 7 | 3 | [5 empty] | 0 |  | 0 | 0
Area 7 | 4 | [5 empty] | 0 |  | 0 | 0
Area 7 | 5 | [5 empty] | 0 |  | 0 | 0
Area 7 | 6 | [5 empty] | 0 |  | 0 | 0
Area 7 — Subtotal | [6 empty] | 358 |  | 100 | 458
Gateway Center (151 Sunny Isles Blvd) | [5 empty] | Section Subtotal → |  |  |  | 641
Area 8 | 1 | Interior - 7.5' Christmas Tree Doublas Fir with WW LED Bulbs 5mm | 1 | Display Sales | indoor tree | 541 | 541 | 100 | 100 | 641 | Completed
Area 8 | 2 | [5 empty] | 0 |  | 0 | 0
Area 8 | 3 | [5 empty] | 0 |  | 0 | 0
Area 8 | 4 | [5 empty] | 0 |  | 0 | 0
Area 8 | 5 | [5 empty] | 0 |  | 0 | 0
Area 8 | 6 | [5 empty] | 0 |  | 0 | 0
Area 8 — Subtotal | [6 empty] | 541 |  | 100 | 641
AREA 9 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 9 | 1 | [5 empty] | 0 |  | 0 | 0
Area 9 | 2 | [5 empty] | 0 |  | 0 | 0
Area 9 | 3 | [5 empty] | 0 |  | 0 | 0
Area 9 | 4 | [5 empty] | 0 |  | 0 | 0
Area 9 | 5 | [5 empty] | 0 |  | 0 | 0
Area 9 | 6 | [5 empty] | 0 |  | 0 | 0
Area 9 — Subtotal | [6 empty] | 0 |  | 0 | 0
AREA 10 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 10 | 1 | [5 empty] | 0 |  | 0 | 0
Area 10 | 2 | [5 empty] | 0 |  | 0 | 0
Area 10 | 3 | [5 empty] | 0 |  | 0 | 0
Area 10 | 4 | [5 empty] | 0 |  | 0 | 0
Area 10 | 5 | [5 empty] | 0 |  | 0 | 0
Area 10 | 6 | [5 empty] | 0 |  | 0 | 0
Area 10 — Subtotal | [6 empty] | 0 |  | 0 | 0
LOGISTICS | [5 empty] | Section Subtotal → |  |  |  | 2192
Logistics | 1 | Shipping | 1 | Display Sales |  | 192 | 192 |  | 0 | 192 | Completed
Logistics | 2 | Storage | 1 | Be The Light |  |  | 0 | 2000 | 2000 | 2000 | Completed
Logistics | 3 | [5 empty] | 0 |  | 0 | 0
Logistics | 4 | [5 empty] | 0 |  | 0 | 0
Logistics — Subtotal | [6 empty] | 192 |  | 2000 | 2192
GRAND TOTAL (All Areas + Logistics) | [5 empty] | Total → |  |  |  | 53599
51407

## Group 3&4 (hidden)
VENDOR DECORATION PROJECT TRACKER
Project: | Sunny Islea Beac FL |  |  |  | Client: |  |  |  |  | PM / Owner:
Start Date: |  |  |  |  | Install Date: | By 11/12 |  |  |  | Currency: | USD
Area | # | Decoration | Qty | Vendor | Link | Material Pricing |  | Labor Pricing |  | Item Total | Status | Approval | Notes | Last Updated
[6 empty] | Unit | Total | Unit | Total
[6 empty] | Section Subtotal → |  |  |  | 0
Area 1 | 1 | [5 empty] | 0 |  | 0 | 0 |  |  | 174th Street – Pole Décor
Area 1 | 2 | [5 empty] | 0 |  | 0 | 0 |  |  | 172nd Street – Pole Décor
Area 1 | 3 | [5 empty] | 0 |  | 0 | 0 |  |  | 163rd - Pole Decor
Area 1 | 4 | [5 empty] | 0 |  | 0 | 0 |  |  | 159th - Pole Decor
Area 1 | 5 | [5 empty] | 0 |  | 0 | 0 |  |  | Monument Signs- 9
Area 1 | 6 | [5 empty] | 0 |  | 0 | 0 |  |  | Intracoastal Sports Park – Façade
Area 1 | 7 | [5 empty] | 0 |  | 0 | 0 |  |  | Norht Bay Road
Area 1 | 8 | [5 empty] | 0 |  | 0 | 0 |  |  | North Bay Road Pedestrian Bridget
Area 1 — Subtotal | [6 empty] | 0 |  | 0 | 0
Group 4 Event at Gateway Park | [5 empty] | Section Subtotal → |  |  |  | 0
Area 2 | 3 | Light & Music Display - Hunter - lmk what you have for sound setups and what (if any) dx need to go with it, otherwise we'll no bid this group | 1 | Be The Light |  |  | 0 |  | 0 | 0 |  |  | Open to proposal – light/music display that can be repeated nightly for up to 2 weeks, minimal damage to lawn. To be up for approximately 2 – 3 weeks.
Area 2 | 4 | [5 empty] | 0 |  | 0 | 0
Area 2 | 5 | [5 empty] | 0 |  | 0 | 0
Area 2 | 6 | [5 empty] | 0 |  | 0 | 0
Area 2 | 7 | [5 empty] | 0 |  | 0 | 0
Area 2 | 8 | [5 empty] | 0 |  | 0 | 0
Area 2 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 3 | 3 | [5 empty] | 0 |  | 0 | 0
Area 3 | 4 | [5 empty] | 0 |  | 0 | 0
Area 3 | 5 | [5 empty] | 0 |  | 0 | 0
Area 3 | 6 | [5 empty] | 0 |  | 0 | 0
Area 3 | 7 | [5 empty] | 0 |  | 0 | 0
Area 3 | 8 | [5 empty] | 0 |  | 0 | 0
Area 3 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 4 | 3 | [5 empty] | 0 |  | 0 | 0
Area 4 | 4 | [5 empty] | 0 |  | 0 | 0
Area 4 | 5 | [5 empty] | 0 |  | 0 | 0
Area 4 | 6 | [5 empty] | 0 |  | 0 | 0
Area 4 | 7 | [5 empty] | 0 |  | 0 | 0
Area 4 | 8 | [5 empty] | 0 |  | 0 | 0
Area 4 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 5 | 3 | [5 empty] | 0 |  | 0 | 0
Area 5 | 4 | [5 empty] | 0 |  | 0 | 0
Area 5 | 5 | [5 empty] | 0 |  | 0 | 0
Area 5 | 6 | [5 empty] | 0 |  | 0 | 0
Area 5 | 7 | [5 empty] | 0 |  | 0 | 0
Area 5 | 8 | [5 empty] | 0 |  | 0 | 0
Area 5 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 6 | 3 | [5 empty] | 0 |  | 0 | 0
Area 6 | 4 | [5 empty] | 0 |  | 0 | 0
Area 6 | 5 | [5 empty] | 0 |  | 0 | 0
Area 6 | 6 | [5 empty] | 0 |  | 0 | 0
Area 6 | 7 | [5 empty] | 0 |  | 0 | 0
Area 6 | 8 | [5 empty] | 0 |  | 0 | 0
Area 6 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 7 | 3 | [5 empty] | 0 |  | 0 | 0
Area 7 | 4 | [5 empty] | 0 |  | 0 | 0
Area 7 | 5 | [5 empty] | 0 |  | 0 | 0
Area 7 | 6 | [5 empty] | 0 |  | 0 | 0
Area 7 | 7 | [5 empty] | 0 |  | 0 | 0
Area 7 | 8 | [5 empty] | 0 |  | 0 | 0
Area 7 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
[7 empty] | 0 |  | 0 | 0
Area 8 | 4 | [5 empty] | 0 |  | 0 | 0
Area 8 | 5 | [5 empty] | 0 |  | 0 | 0
Area 8 | 6 | [5 empty] | 0 |  | 0 | 0
Area 8 | 7 | [5 empty] | 0 |  | 0 | 0
Area 8 | 8 | [5 empty] | 0 |  | 0 | 0
Area 8 — Subtotal | [6 empty] | 0 |  | 0 | 0
AREA 9 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 9 | 3 | [5 empty] | 0 |  | 0 | 0
Area 9 | 4 | [5 empty] | 0 |  | 0 | 0
Area 9 | 5 | [5 empty] | 0 |  | 0 | 0
Area 9 | 6 | [5 empty] | 0 |  | 0 | 0
Area 9 | 7 | [5 empty] | 0 |  | 0 | 0
Area 9 | 8 | [5 empty] | 0 |  | 0 | 0
Area 9 — Subtotal | [6 empty] | 0 |  | 0 | 0
AREA 10 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 10 | 3 | [5 empty] | 0 |  | 0 | 0
Area 10 | 4 | [5 empty] | 0 |  | 0 | 0
Area 10 | 5 | [5 empty] | 0 |  | 0 | 0
Area 10 | 6 | [5 empty] | 0 |  | 0 | 0
Area 10 | 7 | [5 empty] | 0 |  | 0 | 0
Area 10 | 8 | [5 empty] | 0 |  | 0 | 0
Area 10 — Subtotal | [6 empty] | 0 |  | 0 | 0
LOGISTICS | [5 empty] | Section Subtotal → |  |  |  | 0
Logistics | 3 | Shipping | 1 | Display Sales |  |  | 0 |  | 0 | 0
Logistics | 4 | Storage | 1 | Be The Light |  |  | 0 |  | 0 | 0
Logistics | 5 | [5 empty] | 0 |  | 0 | 0
Logistics | 6 | [5 empty] | 0 |  | 0 | 0
Logistics — Subtotal | [6 empty] | 0 |  | 0 | 0
GRAND TOTAL (All Areas + Logistics) | [5 empty] | Total → |  |  |  | 0

## Copy of Sunny Isles Group 1 (51
VENDOR DECORATION PROJECT TRACKER
Project: | Sunny Islea Beac FL |  |  |  | Client: |  |  |  |  | PM / Owner:
Start Date: |  |  |  |  | Install Date: | By 11/12 |  |  |  | Currency: | USD
Area | # | Decoration | Qty | Vendor | Link | Material Pricing |  | Labor Pricing |  | Item Total | Status | Approval | Notes | Last Updated
[6 empty] | Unit | Total | Unit | Total
c | [5 empty] | Section Subtotal → |  |  |  | 68410
Area 1 | 1 | Medjool Palm Trees (Medium) | 56 | Be The Light |  |  | 0 | 240 | 13440 | 13440 | Completed |  | 6 strands each tree. 6*40 = 240 per tree
Area 1 | 2 | Royal Palm Trees | 92 | Be The Light |  |  | 0 | 320 | 29440 | 29440 | Completed |  | 8 strands each tree 8*40 = 320 per tree
Area 1 | 3 | 6' Candy Cane Swirl PM | 15 | Display Sales | CC Swirl | 323 | 4845 | 100 | 1500 | 6345 | Completed |  | PM STANDS FOR POLE MOUNT
Area 1 | 4 | 6' Gift Box PM | 15 | Display Sales | Gift box | 333 | 4995 | 100 | 1500 | 6495 | Completed
Area 1 | 5 | 6' Snowman PM | 15 | Display Sales | https://displaysales.com/products/6-ft-snowman-christmas-pole-mounted-decoration?variant=52151903191221 | 351 | 5265 | 100 | 1500 | 6765 | Completed
Area 1 | 6 | 6' Zig Zag Tree PM | 15 | Display Sales | zig zag | 295 | 4425 | 100 | 1500 | 5925 | Completed
Area 1 | 7 | 6' Double Poinsettia PM | 15 | Display Sales | double poinsettia | 317 | 4755 | 100 | 1500 | 6255 | Completed
Area 1 | 8 | 6' Single Bell PM | 15 | Display Sales | single bell | 304 | 4560 | 100 | 1500 | 6060 | Completed
Area 1 | 9 | 6' Stocking PM | 15 | Display Sales | stocking | 279 | 4185 | 100 | 1500 | 5685 | Completed
Area 1 | 10 | 6' Angel with Halo PM | 14 | Display Sales | angel | 339 | 4746 | 100 | 1400 | 6146 | Completed
Area 1 | 11 | 6' Candy Cane with Bow PM | 14 | Display Sales | candy cane w bow | 304 | 4256 | 100 | 1400 | 5656 | Completed
Area 1 | 12 | 6; Candle with Halo PM | 14 | Display Sales | candle w halo | 278 | 3892 | 100 | 1400 | 5292 | Completed
Area 1 | 13 | 6 Toy Soldier PM | 14 | Display Sales | toy soldier | 346 | 4844 | 100 | 1400 | 6244 | Completed
Area 1 — Subtotal | [6 empty] | 19530 |  | 48880 | 68410
Sunny Isles East Boulevard (163rd St E Bound) | [5 empty] | Section Subtotal → |  |  |  | 23117
Area 2 | 8 | Medjool Palm Trees | 65 | Be The Light |  |  | 0 | 240 | 15600 | 15600 | Completed
Area 2 | 9 | Various Palms | 1 | Be The Light |  |  | 0 | 1000 | 1000 | 1000 | Completed
Area 2 | 10 | 6' Reindeer PM | 5 | Display Sales | reindeer | 323 | 1615 | 100 | 100 | 1715 | Completed
Area 2 | 11 | 6' Christmas Tree PM | 5 | Display Sales | xmas tree | 254 | 1270 | 100 | 500 | 1770 | Completed
Area 2 | 12 | 6' Candy Cane Swirl PM | 4 | Display Sales | CC Swirl | 323 | 1292 | 100 | 400 | 1692 | Completed
Area 2 | 13 | 6' Stocking PM | 4 | Display Sales | stocking | 235 | 940 | 100 | 400 | 1340 | Completed
Area 2 — Subtotal | [6 empty] | 5117 |  | 18000 | 23117
Enterances | [5 empty] | Section Subtotal → |  |  |  | 3000
Area 3 | 1 | North Entrance: Palm Tree with Ornaments | 2 | Display Sales | palm with ornaments | 400 | 800 | 100 | 200 | 1000 |  |  | nowhere does this list the addresses for any of these enterances, these dx can be pole munted/ground mounted/or wall mounted and will be built to best fit each space
Area 3 | 2 | Wiilliam Lehman Causeway Entrance: Palm Tree with Ornaments | 2 | Display Sales | palm with ornaments | 400 | 800 | 100 | 200 | 1000
Area 3 | 3 | South City Entrance: Palm Tree with Ornaments | 2 | Display Sales | palm with ornaments | 400 | 800 | 100 | 200 | 1000
Area 6 | -16 | [5 empty] | 0 |  | 0 | 0
Area 6 | -15 | [5 empty] | 0 |  | 0 | 0
Area 6 | -14 | [5 empty] | 0 |  | 0 | 0
Area 6 — Subtotal | [6 empty] | 2400 |  | 600 | 3000
Gateway Park (151 Sunny Isles Blvd) | [5 empty] | Section Subtotal → |  |  |  | 66026
Area 4 | 1 | Oak Trees (trunk & canopy) | 22 | Be The Light |  |  | 0 | 600 | 13200 | 13200 | Completed |  | 15 strands per tree *40 per strand = 600/
Area 4 | 2 | Date Palms | 8 | Be The Light |  |  | 0 | 240 | 1920 | 1920 | Completed |  | 6 strands each tree. 6*40 = 240 per tree
Area 4 | 3 | 6' Menorah Ground Mount | 1 | Display Sales | menorah | 721 | 721 | 100 | 100 | 821 | Completed
Area 4 | 4 | 17' Walkthrough Package with Bow | 1 | Display Sales | Walkthrough package | 17415 | 17415 | 500 | 500 | 17915 | Completed
Area 4 | 5 | 34' Panel Tree | 1 | Display Sales | panel tree | 28188 | 28188 | 3000 | 3000 | 31188 | Completed
Area 4 | 6 | 4' 3D Nativity Star Top | 1 | Display Sales | tree topper | 882 | 882 | 100 | 100 | 982 | Completed
Area 4 | 7 | 10' Santa Deluxe Sleigh Photo Op | 1 | Display Sales | Sleigh | 21560 | 21560 | 250 | 250 | 21810 | Completed
Area 6 — Subtotal | [6 empty] | 47206 |  | 18820 | 66026
Area 8 | 10 | [5 empty] | 0 |  | 0 | 0
Area 8 | 11 | [5 empty] | 0 |  | 0 | 0
Area 8 | 12 | [5 empty] | 0 |  | 0 | 0
Area 8 | 13 | [5 empty] | 0 |  | 0 | 0
Area 8 | 14 | [5 empty] | 0 |  | 0 | 0
AREA 9 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 9 | 9 | [5 empty] | 0 |  | 0 | 0
Area 9 | 10 | [5 empty] | 0 |  | 0 | 0
Area 9 | 11 | [5 empty] | 0 |  | 0 | 0
Area 9 | 12 | [5 empty] | 0 |  | 0 | 0
Area 9 | 13 | [5 empty] | 0 |  | 0 | 0
Area 9 | 14 | [5 empty] | 0 |  | 0 | 0
Area 9 — Subtotal | [6 empty] | 0 |  | 0 | 0
AREA 10 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 10 | 9 | [5 empty] | 0 |  | 0 | 0
Area 10 | 10 | [5 empty] | 0 |  | 0 | 0
Area 10 | 11 | [5 empty] | 0 |  | 0 | 0
Area 10 | 12 | [5 empty] | 0 |  | 0 | 0
Area 10 | 13 | [5 empty] | 0 |  | 0 | 0
Area 10 | 14 | [5 empty] | 0 |  | 0 | 0
Area 10 — Subtotal | [6 empty] | 0 |  | 0 | 0
LOGISTICS | [5 empty] | Section Subtotal → |  |  |  | 23517
Logistics | 9 | Shipping | 1 | Display Sales |  | 13517 | 13517 |  | 0 | 13517 | Completed
Logistics | 10 | Storage | 1 | Be The Light |  |  | 0 | 8000 | 8000 | 8000 | Completed
Logistics | 11 | Maintenance | 1 |  |  |  | 0 | 2000 | 2000 | 2000
Logistics | 12 | [5 empty] | 0 |  | 0 | 0
Logistics — Subtotal | [6 empty] | 13517 |  | 10000 | 23517
GRAND TOTAL (All Areas + Logistics) | [5 empty] | Total → |  |  |  | 184070
368140
-
[6 empty] | MATERIAL | #REF!
[6 empty] | SHIPPING | 13517

## Copy of Sunny Isles Group 2 (51
VENDOR DECORATION PROJECT TRACKER
Project: | Sunny Islea Beac FL |  |  |  | Client: |  |  |  |  | PM / Owner:
Start Date: |  |  |  |  | Install Date: | By 11/12 |  |  |  | Currency: | USD
Area | # | Decoration | Qty | Vendor | Link | Material Pricing |  | Labor Pricing |  | Item Total | Status | Approval | Notes | Last Updated
[6 empty] | Unit | Total | Unit | Total
Park Lighting - Heritage Park (19200 Collins Ave) | [5 empty] | Section Subtotal → |  |  |  | 7360
Area 1 | 1 | Medjool Palm Trees (Trunk & Fronds) | 26 | Be The Light |  |  | 0 | 240 | 6240 | 6240 | Completed |  | 6 strands each tree. 6*40 = 240 per tree
Area 1 | 2 | Fountain Wall Decoration - Custom "SUNNY ISLES" wall or ground mount decoration, wrapped in metallic garland and illuminated with C-7 Bulbs | 1 | Display Sales |  | 920 | 920 | 200 | 200 | 1120
Area 1 | 3 | [5 empty] | 0 |  | 0 | 0
Area 1 | 4 | [5 empty] | 0 |  | 0 | 0
Area 1 | 5 | [5 empty] | 0 |  | 0 | 0
Area 1 | 6 | [5 empty] | 0 |  | 0 | 0
Area 1 — Subtotal | [6 empty] | 920 |  | 6440 | 7360
Park Lighting - Samson Park (17425 Collins Ave) | [5 empty] | Section Subtotal → |  |  |  | 12240
Area 2 | 1 | Medjool Palm Trees (trunk & fronds) | 11 | Be The Light |  |  | 0 | 240 | 2640 | 2640 | Completed
Area 2 | 2 | Palm Trees (coconut/triple christmas) | 40 | Be The Light |  |  | 0 | 240 | 9600 | 9600 | Completed
Area 2 | 3 | [5 empty] | 0 |  | 0 | 0
Area 2 | 4 | [5 empty] | 0 |  | 0 | 0
Area 2 | 5 | [5 empty] | 0 |  | 0 | 0
Area 2 | 6 | [5 empty] | 0 |  | 0 | 0
Area 2 — Subtotal | [6 empty] | 0 |  | 12240 | 12240
Park Lighting - Intracoastal SPorts Park (Collins Ave 159 to 163rd St) | [5 empty] | Section Subtotal → |  |  |  | 0
Area 3 | 1 | OPTIONAL Tree Lighting - Open to Proposal |  | Be The Light |  |  | 0 |  | 0 | 0
Area 3 | 2 | [5 empty] | 0 |  | 0 | 0
Area 3 | 3 | [5 empty] | 0 |  | 0 | 0
Area 3 | 4 | [5 empty] | 0 |  | 0 | 0
Area 3 | 5 | [5 empty] | 0 |  | 0 | 0
Area 3 | 6 | [5 empty] | 0 |  | 0 | 0
Area 3 — Subtotal | [6 empty] | 0 |  | 0 | 0
Park Lighting - The Spot (215 185th St) | [5 empty] | Section Subtotal → |  |  |  | 1230
Area 4 | 1 | Medjool Palm Trees (trunk & fronds) | 2 | Be The Light |  |  | 0 | 240 | 480 | 480 | Completed
Area 4 | 2 | Lights on front Building facade | 1 | Be The Light |  |  | 0 | 750 | 750 | 750 | Completed
Area 4 | 3 | [5 empty] | 0 |  | 0 | 0
Area 4 | 4 | [5 empty] | 0 |  | 0 | 0
Area 4 | 5 | [5 empty] | 0 |  | 0 | 0
Area 4 | 6 | [5 empty] | 0 |  | 0 | 0
Area 4 — Subtotal | [6 empty] | 0 |  | 1230 | 1230
Town Center Park (17200 Colins Ave) | [5 empty] | Section Subtotal → |  |  |  | 9000
Area 5 | 1 | OPTIONAL Tree Lighting - Open to Proposal | 30 | Be The Light |  |  | 0 | 300 | 9000 | 9000 | Completed
Area 5 | 2 | [5 empty] | 0 |  | 0 | 0
Area 5 | 3 | [5 empty] | 0 |  | 0 | 0
Area 5 | 4 | [5 empty] | 0 |  | 0 | 0
Area 5 | 5 | [5 empty] | 0 |  | 0 | 0
Area 5 | 6 | [5 empty] | 0 |  | 0 | 0
Area 5 — Subtotal | [6 empty] | 0 |  | 9000 | 9000
Facilities - Government Center (18070 Colins Ave) | [5 empty] | Section Subtotal → |  |  |  | 2698
Area 6 | 1 | Exterior - Medjool Palm (trunk&frond) | 6 | Be The Light |  |  | 0 | 300 | 1800 | 1800 | Completed
Area 6 | 2 | Indoor - 10' Christmas Tree Douglas Fir with WW LED Bulbs 5mm | 1 | Display Sales | indoor tree | 698 | 698 | 200 | 200 | 898 | Completed
Area 6 | 3 | [5 empty] | 0 |  | 0 | 0
Area 6 | 4 | [5 empty] | 0 |  | 0 | 0
Area 6 | 5 | [5 empty] | 0 |  | 0 | 0
Area 6 | 6 | [5 empty] | 0 |  | 0 | 0
Area 6 — Subtotal | [6 empty] | 698 |  | 2000 | 2698
Facilities - Palican Community Park (18155 North Bay Road) | [5 empty] | Section Subtotal → |  |  |  | 458
Area 7 | 1 | Interior - 6.5' Christmas Tree Douglas Fir with WW LED Bulbs 5mm | 1 | Display Sales | indoor tree | 358 | 358 | 100 | 100 | 458 | Completed
Area 7 | 2 | [5 empty] | 0 |  | 0 | 0
Area 7 | 3 | [5 empty] | 0 |  | 0 | 0
Area 7 | 4 | [5 empty] | 0 |  | 0 | 0
Area 7 | 5 | [5 empty] | 0 |  | 0 | 0
Area 7 | 6 | [5 empty] | 0 |  | 0 | 0
Area 7 — Subtotal | [6 empty] | 358 |  | 100 | 458
Facilities - Gateway Center (151 Sunny Isles Blvd) | [5 empty] | Section Subtotal → |  |  |  | 641
Area 8 | 1 | Interior - 7.5' Christmas Tree Doublas Fir with WW LED Bulbs 5mm | 1 | Display Sales | indoor tree | 541 | 541 | 100 | 100 | 641 | Completed
Area 8 | 2 | [5 empty] | 0 |  | 0 | 0
Area 8 | 3 | [5 empty] | 0 |  | 0 | 0
Area 8 | 4 | [5 empty] | 0 |  | 0 | 0
Area 8 | 5 | [5 empty] | 0 |  | 0 | 0
Area 8 | 6 | [5 empty] | 0 |  | 0 | 0
Area 8 — Subtotal | [6 empty] | 541 |  | 100 | 641
AREA 9 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 9 | 1 | [5 empty] | 0 |  | 0 | 0
Area 9 | 2 | [5 empty] | 0 |  | 0 | 0
Area 9 | 3 | [5 empty] | 0 |  | 0 | 0
Area 9 | 4 | [5 empty] | 0 |  | 0 | 0
Area 9 | 5 | [5 empty] | 0 |  | 0 | 0
Area 9 | 6 | [5 empty] | 0 |  | 0 | 0
Area 9 — Subtotal | [6 empty] | 0 |  | 0 | 0
AREA 10 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 10 | 1 | [5 empty] | 0 |  | 0 | 0
Area 10 | 2 | [5 empty] | 0 |  | 0 | 0
Area 10 | 3 | [5 empty] | 0 |  | 0 | 0
Area 10 | 4 | [5 empty] | 0 |  | 0 | 0
Area 10 | 5 | [5 empty] | 0 |  | 0 | 0
Area 10 | 6 | [5 empty] | 0 |  | 0 | 0
Area 10 — Subtotal | [6 empty] | 0 |  | 0 | 0
LOGISTICS | [5 empty] | Section Subtotal → |  |  |  | 2380
Logistics | 1 | Shipping | 1 | Display Sales |  | 380 | 380 |  | 0 | 380 | Completed
Logistics | 2 | Storage | 1 | Be The Light |  |  | 0 | 2000 | 2000 | 2000 | Completed
Logistics | 3 | [5 empty] | 0 |  | 0 | 0
Logistics | 4 | [5 empty] | 0 |  | 0 | 0
Logistics — Subtotal | [6 empty] | 380 |  | 2000 | 2380
GRAND TOTAL (All Areas + Logistics) | [5 empty] | Total → |  |  |  | 36007

## Copy of Sunny Isles Group 3 (51
VENDOR DECORATION PROJECT TRACKER
Project: | Sunny Islea Beac FL |  |  |  | Client: |  |  |  |  | PM / Owner:
Start Date: |  |  |  |  | Install Date: | By 11/12 |  |  |  | Currency: | USD
Area | # | Decoration | Qty | Vendor | Link | Material Pricing |  | Labor Pricing |  | Item Total | Status | Approval | Notes | Last Updated
[6 empty] | Unit | Total | Unit | Total
Right-Of-Ways - 74th Street | [5 empty] | Section Subtotal → |  |  |  | 7866
Area 1 | 1 | 6' Candy Cane Swirl PM | 10 | Display Sales | CC Swirl | 323 | 3230 | 100 | 1000 | 4230 | Completed
Area 1 | 2 | 6' Candy Cane Bow PM | 9 | Display Sales | candy cane w bow | 304 | 2736 | 100 | 900 | 3636 | Completed
Area 5 | -33 | [5 empty] | 0 |  | 0 | 0
Area 5 | -32 | [5 empty] | 0 |  | 0 | 0
Area 5 | -31 | [5 empty] | 0 |  | 0 | 0
Area 5 | -30 | [5 empty] | 0 |  | 0 | 0
Area 5 — Subtotal | [6 empty] | 5966 |  | 1900 | 7866
Right-Of-Ways - 172nd Street | [5 empty] | Section Subtotal → |  |  |  | 4606
Area 2 | 1 | 4' Diamond Snow flakes PM | 14 | Display Sales | diamond | 229 | 3206 | 100 | 1400 | 4606 | Completed
Area 4 | -16 | [5 empty] | 0 |  | 0 | 0
Area 4 | -15 | [5 empty] | 0 |  | 0 | 0
Area 4 | -14 | [5 empty] | 0 |  | 0 | 0
Area 4 | -13 | [5 empty] | 0 |  | 0 | 0
Area 4 | -12 | [5 empty] | 0 |  | 0 | 0
Area 4 — Subtotal | [6 empty] | 3206 |  | 1400 | 4606
Right-Of-Ways - North Bay Road (between 172nd St & 163rd St) | [5 empty] | Section Subtotal → |  |  |  | 7087
Area 3 | 1 | 5.5' 4 Falling Star PMs | 19 | Display Sales | falling stars | 273 | 5187 | 100 | 1900 | 7087 | Completed
Area 3 | 2 | [5 empty] | 0 |  | 0 | 0
Area 3 | 3 | [5 empty] | 0 |  | 0 | 0
Area 3 | 4 | [5 empty] | 0 |  | 0 | 0
Area 3 | 5 | [5 empty] | 0 |  | 0 | 0
Area 3 | 6 | [5 empty] | 0 |  | 0 | 0
Area 3 — Subtotal | [6 empty] | 5187 |  | 1900 | 7087
Right-Of-Ways - Kings Point Drive (159th St as Labeled on Map) | [5 empty] | Section Subtotal → |  |  |  | 4194
Area 4 | 1 | 6' Triple Star PM | 9 | Display Sales | triple star | 366 | 3294 | 100 | 900 | 4194 | Completed
Area 7 | -25 | [5 empty] | 0 |  | 0 | 0
Area 7 | -24 | [5 empty] | 0 |  | 0 | 0
Area 7 | -23 | [5 empty] | 0 |  | 0 | 0
Area 7 | -22 | [5 empty] | 0 |  | 0 | 0
Area 7 | -21 | [5 empty] | 0 |  | 0 | 0
Area 7 — Subtotal | [6 empty] | 3294 |  | 900 | 4194
Right-Of-Ways - Padestrian Bridge (163 WB) | [5 empty] | Section Subtotal → |  |  |  | #REF!
Area 5 | 1 | 4' Designer Star | 8 | Display Sales | designer star | 234 | 1872 | 100 | 800 | 2672 | Completed
Area 8 — Subtotal | [6 empty] | 1872 |  | 800 | 2672
Right-Of-Ways - Padestrian Bridge (Between 174th ST & 172nd ST) | [5 empty] | Section Subtotal → |  |  |  | #REF!
Area 6 | 1 | 4' Designer Star | 8 | Display Sales | designer star | 234 | 1872 | 100 | 800 | 2672 | Completed
Area 8 — Subtotal | [6 empty] | 1872 |  | 800 | 2672
Monument Signs - 9 locations
Area 7 | 1 | 5' Fancy Fork Snowflakes Ground Mounts, 2 per location | 18 | Display Sales | ff snowflake | 295 | 5310 | 100 | 1800 | 7110
[7 empty] | 5310 |  | 1800 | 7110
Intracoastal Sports Park - Facade | [5 empty] | Section Subtotal → |  |  |  | 0
Area 3 | 36 | Roofline lighting |  | Be The Light | being built right now - photo from march 10th |  | 0 |  | 0 | 0
Area 3 | 37 | [5 empty] | 0 |  | 0 | 0
Area 3 | 38 | [5 empty] | 0 |  | 0 | 0
Area 3 | 39 | [5 empty] | 0 |  | 0 | 0
Area 3 | 40 | [5 empty] | 0 |  | 0 | 0
Area 3 | 41 | [5 empty] | 0 |  | 0 | 0
Area 3 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 4 | 36 | [5 empty] | 0 |  | 0 | 0
Area 4 | 37 | [5 empty] | 0 |  | 0 | 0
Area 4 | 38 | [5 empty] | 0 |  | 0 | 0
Area 4 | 39 | [5 empty] | 0 |  | 0 | 0
Area 4 | 40 | [5 empty] | 0 |  | 0 | 0
Area 4 | 41 | [5 empty] | 0 |  | 0 | 0
Area 4 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 5 | 36 | [5 empty] | 0 |  | 0 | 0
Area 5 | 37 | [5 empty] | 0 |  | 0 | 0
Area 5 | 38 | [5 empty] | 0 |  | 0 | 0
Area 5 | 39 | [5 empty] | 0 |  | 0 | 0
Area 5 | 40 | [5 empty] | 0 |  | 0 | 0
Area 5 | 41 | [5 empty] | 0 |  | 0 | 0
Area 5 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 6 | 36 | [5 empty] | 0 |  | 0 | 0
Area 6 | 37 | [5 empty] | 0 |  | 0 | 0
Area 6 | 38 | [5 empty] | 0 |  | 0 | 0
Area 6 | 39 | [5 empty] | 0 |  | 0 | 0
Area 6 | 40 | [5 empty] | 0 |  | 0 | 0
Area 6 | 41 | [5 empty] | 0 |  | 0 | 0
Area 6 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 7 | 36 | [5 empty] | 0 |  | 0 | 0
Area 7 | 37 | [5 empty] | 0 |  | 0 | 0
Area 7 | 38 | [5 empty] | 0 |  | 0 | 0
Area 7 | 39 | [5 empty] | 0 |  | 0 | 0
Area 7 | 40 | [5 empty] | 0 |  | 0 | 0
Area 7 | 41 | [5 empty] | 0 |  | 0 | 0
Area 7 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
[7 empty] | 0 |  | 0 | 0
Area 8 | 37 | [5 empty] | 0 |  | 0 | 0
Area 8 | 38 | [5 empty] | 0 |  | 0 | 0
Area 8 | 39 | [5 empty] | 0 |  | 0 | 0
Area 8 | 40 | [5 empty] | 0 |  | 0 | 0
Area 8 | 41 | [5 empty] | 0 |  | 0 | 0
Area 8 — Subtotal | [6 empty] | 0 |  | 0 | 0
AREA 9 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 9 | 36 | [5 empty] | 0 |  | 0 | 0
Area 9 | 37 | [5 empty] | 0 |  | 0 | 0
Area 9 | 38 | [5 empty] | 0 |  | 0 | 0
Area 9 | 39 | [5 empty] | 0 |  | 0 | 0
Area 9 | 40 | [5 empty] | 0 |  | 0 | 0
Area 9 | 41 | [5 empty] | 0 |  | 0 | 0
Area 9 — Subtotal | [6 empty] | 0 |  | 0 | 0
AREA 10 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 10 | 36 | [5 empty] | 0 |  | 0 | 0
Area 10 | 37 | [5 empty] | 0 |  | 0 | 0
Area 10 | 38 | [5 empty] | 0 |  | 0 | 0
Area 10 | 39 | [5 empty] | 0 |  | 0 | 0
Area 10 | 40 | [5 empty] | 0 |  | 0 | 0
Area 10 | 41 | [5 empty] | 0 |  | 0 | 0
Area 10 — Subtotal | [6 empty] | 0 |  | 0 | 0
LOGISTICS | [5 empty] | Section Subtotal → |  |  |  | 4000
Logistics | 36 | Shipping | 1 | Display Sales |  | 4000 | 4000 |  | 0 | 4000
Logistics | 37 | Storage | 1 | Be The Light |  |  | 0 |  | 0 | 0
Logistics | 38 | [5 empty] | 0 |  | 0 | 0
Logistics | 39 | [5 empty] | 0 |  | 0 | 0
Logistics — Subtotal | [6 empty] | 4000 |  | 0 | 4000
GRAND TOTAL (All Areas + Logistics) | [5 empty] | Total → |  |  |  | 40207

## Copy of Sunny Isles Group 4 (51
VENDOR DECORATION PROJECT TRACKER
Project: | Sunny Islea Beac FL |  |  |  | Client: |  |  |  |  | PM / Owner:
Start Date: |  |  |  |  | Install Date: | By 11/12 |  |  |  | Currency: | USD
Area | # | Decoration | Qty | Vendor | Link | Material Pricing |  | Labor Pricing |  | Item Total | Status | Approval | Notes | Last Updated
[6 empty] | Unit | Total | Unit | Total
Group 4 Event at Gateway Park | [5 empty] | Section Subtotal → |  |  |  | 0
Area 2 | 1 | Light & Music Display - Hunter - lmk what you have for sound setups and what (if any) dx need to go with it, otherwise we'll no bid this group | 1 | Be The Light |  |  | 0 |  | 0 | 0 |  |  | Open to proposal – light/music display that can be repeated nightly for up to 2 weeks, minimal damage to lawn. To be up for approximately 2 – 3 weeks.
Area 2 | -6 | [5 empty] | 0 |  | 0 | 0
Area 2 | -5 | [5 empty] | 0 |  | 0 | 0
Area 2 | -4 | [5 empty] | 0 |  | 0 | 0
Area 2 | -3 | [5 empty] | 0 |  | 0 | 0
Area 2 | -2 | [5 empty] | 0 |  | 0 | 0
Area 2 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 3 | -7 | [5 empty] | 0 |  | 0 | 0
Area 3 | -6 | [5 empty] | 0 |  | 0 | 0
Area 3 | -5 | [5 empty] | 0 |  | 0 | 0
Area 3 | -4 | [5 empty] | 0 |  | 0 | 0
Area 3 | -3 | [5 empty] | 0 |  | 0 | 0
Area 3 | -2 | [5 empty] | 0 |  | 0 | 0
Area 3 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 4 | -7 | [5 empty] | 0 |  | 0 | 0
Area 4 | -6 | [5 empty] | 0 |  | 0 | 0
Area 4 | -5 | [5 empty] | 0 |  | 0 | 0
Area 4 | -4 | [5 empty] | 0 |  | 0 | 0
Area 4 | -3 | [5 empty] | 0 |  | 0 | 0
Area 4 | -2 | [5 empty] | 0 |  | 0 | 0
Area 4 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 5 | -7 | [5 empty] | 0 |  | 0 | 0
Area 5 | -6 | [5 empty] | 0 |  | 0 | 0
Area 5 | -5 | [5 empty] | 0 |  | 0 | 0
Area 5 | -4 | [5 empty] | 0 |  | 0 | 0
Area 5 | -3 | [5 empty] | 0 |  | 0 | 0
Area 5 | -2 | [5 empty] | 0 |  | 0 | 0
Area 5 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 6 | -7 | [5 empty] | 0 |  | 0 | 0
Area 6 | -6 | [5 empty] | 0 |  | 0 | 0
Area 6 | -5 | [5 empty] | 0 |  | 0 | 0
Area 6 | -4 | [5 empty] | 0 |  | 0 | 0
Area 6 | -3 | [5 empty] | 0 |  | 0 | 0
Area 6 | -2 | [5 empty] | 0 |  | 0 | 0
Area 6 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
Area 7 | -7 | [5 empty] | 0 |  | 0 | 0
Area 7 | -6 | [5 empty] | 0 |  | 0 | 0
Area 7 | -5 | [5 empty] | 0 |  | 0 | 0
Area 7 | -4 | [5 empty] | 0 |  | 0 | 0
Area 7 | -3 | [5 empty] | 0 |  | 0 | 0
Area 7 | -2 | [5 empty] | 0 |  | 0 | 0
Area 7 — Subtotal | [6 empty] | 0 |  | 0 | 0
[6 empty] | Section Subtotal → |  |  |  | 0
[7 empty] | 0 |  | 0 | 0
Area 8 | -6 | [5 empty] | 0 |  | 0 | 0
Area 8 | -5 | [5 empty] | 0 |  | 0 | 0
Area 8 | -4 | [5 empty] | 0 |  | 0 | 0
Area 8 | -3 | [5 empty] | 0 |  | 0 | 0
Area 8 | -2 | [5 empty] | 0 |  | 0 | 0
Area 8 — Subtotal | [6 empty] | 0 |  | 0 | 0
AREA 9 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 9 | -7 | [5 empty] | 0 |  | 0 | 0
Area 9 | -6 | [5 empty] | 0 |  | 0 | 0
Area 9 | -5 | [5 empty] | 0 |  | 0 | 0
Area 9 | -4 | [5 empty] | 0 |  | 0 | 0
Area 9 | -3 | [5 empty] | 0 |  | 0 | 0
Area 9 | -2 | [5 empty] | 0 |  | 0 | 0
Area 9 — Subtotal | [6 empty] | 0 |  | 0 | 0
AREA 10 | [5 empty] | Section Subtotal → |  |  |  | 0
Area 10 | -7 | [5 empty] | 0 |  | 0 | 0
Area 10 | -6 | [5 empty] | 0 |  | 0 | 0
Area 10 | -5 | [5 empty] | 0 |  | 0 | 0
Area 10 | -4 | [5 empty] | 0 |  | 0 | 0
Area 10 | -3 | [5 empty] | 0 |  | 0 | 0
Area 10 | -2 | [5 empty] | 0 |  | 0 | 0
Area 10 — Subtotal | [6 empty] | 0 |  | 0 | 0
LOGISTICS | [5 empty] | Section Subtotal → |  |  |  | 0
Logistics | 2 | Storage | 1 | Be The Light |  |  | 0 |  | 0 | 0
Logistics | [6 empty] | 0 |  | 0 | 0
Logistics | 3 | [5 empty] | 0 |  | 0 | 0
Logistics | 4 | [5 empty] | 0 |  | 0 | 0
Logistics — Subtotal | [6 empty] | 0 |  | 0 | 0
GRAND TOTAL (All Areas + Logistics) | [5 empty] | Total → |  |  |  | #REF!

## Sheet2 (hidden)
66868.13 | 7360 | 7866
42880 | 12240 | 4606
23117 | 1230 | 7087
1000 | 14400 | 4194
1000 | 9000 | 7110
1000 | 2698 | 2672
66026 | 458 | 3322
201891.13 | 643
| 48029 | 36857